## v1.0
Pulse 3.0 ¦ MRSporty (Pert Estimation)
| Task | Optimistic (MH) | MostLikely (MH) | Pessimistic (MH) | E | SD / Task | SD Project | Assumption
Pre Development | Dashboard Understanding | 1 | 2 | 3 | 2 | 0.33333 | 0.11111
| Create Solution for this dashboard and how to manage its data | 6 | 6 | 8 | 6.3333 | 0.33333 | 0.11111
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
Database | Database Architecture Modification | 5 | 6 | 8 | 6.1667 | 0.5 | 0.25
| Create migrations and different tables | 4 | 1 | 6 | 2.3333 | 0.33333 | 0.11111
| Create associations | 1 | 1 | 1 | 1 | 0 | 0
[5 empty] | 0 | 0 | 0
Import | Data Import | 6 | 8 | 10 | 8 | 0.66667 | 0.44444
| Stats computation | 6 | 8 | 10 | 8 | 0.66667 | 0.44444
[5 empty] | 0 | 0 | 0
APIs | Filters | 3 | 4 | 5 | 4 | 0.33333 | 0.11111
| Pie chart data | 4 | 4 | 6 | 4.3333 | 0.33333 | 0.11111
| Report Detail | 6 | 6 | 8 | 6.3333 | 0.33333 | 0.11111
| Club Detail Pie | 6 | 8 | 10 | 8 | 0.66667 | 0.44444
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
Testing | Testing | 3 | 4 | 6 | 4.1667 | 0.5 | 0.25
[5 empty] | 0 | 0 | 0
Improvements | Code optimisation | 3 | 4 | 6 | 4.1667 | 0.5 | 0.25
| Fix bugs | 3 | 4 | 6 | 4.1667 | 0.5 | 0.25
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
| Total ManHours | 57 | 66 | 93
| PERT Estimation (E) | 69
| PERT Confidence | 6
| SD for Total Project work (SD) | 1.7321
124.7077
| Approximately 80% Confidence level in Estimates (ManHours) | 69
| Time to delivery | 11.5 | man days
| Weeks to deliver | 2.3 | weeks